## Product Backlog
Product Name: | MICE Manager | [5 empty] | Complete Fields in Green!!!
Team ID: | Loose Souls
| Team Member Name |  |  |  |  | Initials | Student ID
Required | Brandon Carter |  |  |  |  | BC | 1001350607
Teams Only:
Teams Only:
Teams Only:
Note: Teams MUST be approved by the Professor (NOT TA) in advance
Sprint # | Remaining | Completed This Sprint |  |  | Comment
0 | 41 |  |  | Total | Total number of features (in column H)
1 | 36 | 5 |  | 1 | Total features left at the end of Sprint #1
2 | 32 | 4 |  | 2 | Total features left at the end of Sprint #2
3 | 29 | 3 |  | 3 | ...and so on
4 | 25 | 4
5 | 23 | 2
6 | 10 | 13
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CF | 1 | 1 | 13 | 1 | Finished in Sprint 1 | Manager | Create a new ice cream flavor | Stock and sell dairy products | picture not yet required, just test the classes here w/o GUI
CC | 2 | 1 | 5 | 1 | Finished in Sprint 1 | Manager | Create a new container | Stock and sell dairy products | Picture not yet required
CT | 3 | 1 | 5 | 1 | Finished in Sprint 1 | Manager | Create a new topping | Stock and sell better dairy products | Picture not yet required
GUI | 4 | 2 | 8 | 1 | Finished in Sprint 1 | Manager | Use a GUI instead of a terminal | Reduce training costs | This is the main window, with menu bar, tool bar, and optionally status bar
IGUI | 5 | 2 | 13 | 2 | Finished in Sprint 1 | Manager | Use dialogs to create items | Reduce training costs | One dialog should server for all items with minor variations
CS | 6 | 2 | 8 | 2 | Finished in Sprint 2 | Server | Create a serving of ice cream in a container with toppings | Create dairy products to sell | Pick a container, 1-N scoop flavors, and 0-N toppings via one or more dialogs, instance a serving object, and push on a vector
PS | 7 | 3 | 5 | 2 | Finished in Sprint 2 | Customer | Show the components of a serving (container, scoops, and toppings) for verification | Ensure my order was taken correctly | This is effectively a to_string method to a dialog with confirm or start over buttons
CTM | 8 | 3 | 3 | 3 | Finished in Sprint 2 | Manager | Create a new server | Staff the emporium
CB | 9 | 3 | 2 | 3 | Finished in Sprint 2 | Server | Create a new beloved customer | Keep track of our customers
CO | 10 | 3 | 13 | 3 | Finished in Sprint 3 | Server | Create an order of many servings of ice cream | Serve everyone in a customer party
CSB | 11 | 3 | 1 | 3 | Finished in Sprint 3 | Customer | Create a serving of ice cream in a container with toppings | Self-order and not have to deal with people | This just enables the Customer role to do what the Server can do in defining a serving…
COB | 12 | 3 | 1 | 3 | Finished in Sprint 3 | Customer | Create an order of many servings of ice cream | Self-order and not have to deal with people | ...and order
CE | 13 | 4 | 5 |  | Finished in Sprint 4 | Manager | Create an emporium that stocks items and maintains a cash register | Manage the emporium | This includes item stocks, server and customer lists, and the cash register
MST | 14 | 4 | 8 |  | Finished in Sprint 4 | Manager | Manage the state of each order (unfilled -> filled -> paid, or unfilled -> canceled) | Ensure each order is filled and payment collected
SAVD | 15 | 4 | 8 |  | Finished in Sprint 4 | Manager | Save all data to a default file | Ensure our data isn’t lost
LOAD | 16 | 4 | 5 |  | Finished in Sprint 4 | Manager | Load data from a default file | Ensure our data isn’t lost
POS | 17 | 5 | 5 |  | Finished in Sprint 5 | Server | Show the servings in an order for the servers (what to prepare) | Know what to put into each serving in an order | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
POC | 18 | 5 | 5 |  | Finished in Sprint 5 | Customer | Show the servings in an order for the customer (what was ordered / how much it costs) | Verify that my order was taken correctly and see the price | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
CM | 19 | 6 | 3 |  | Finished in Sprint 6 | Owner | Create a named manager | Delegate management tasks to a pro
P&L | 20 | 6 | 8 |  | Finished in Sprint 6 | Manager | Add a Profit & Loss statement, showing all income, expenses, and total profit | Ensure that we’re making a profit and thus avoid bankruptcy
RI | 21 | 6 | 5 |  | Finished in Sprint 6 | Manager | Display an Inventory Report, listing every item and the quantity in stock | Ensure we don’t run out of any product and thus disappoint our customers
PIX | 22 |  | 21 |  | Finished in Sprint 6 | Customer | Add and display pictures for each item (container, ice cream flavor, and topping) | Better understand the menu
RTM | 23 |  | 8 |  | Finished in Sprint 6 | Manager | Display a Server Report, listing all info about each server including # of orders served | Better manage our team and reward productive team members
ETMS | 24 |  | 8 |  | Finished in Sprint 6 | Manager | Change a server salary | Offer promotions and pay bumps to motivate our team members
AI | 25 |  | 8 |  | Finished in Sprint 6 | Server | Restock items (ice cream flavor, container, and topping) | Ensure we can fill every order
RO | 26 |  | 8 |  | Finished in Sprint 6 | Manager | Create an Order Report, showing all pending orders (unfilled and filled but unpaid) | Better manage our production process
RB | 27 |  | 5 |  | Finished in Sprint 6 | Manager | Display a Customer Report, listing all info about each customer | Better attract repeat customers and handle complaints
EF | 28 |  | 8 |  | Finished in Sprint 6 | Manager | Edit an ice cream flavor | Improve our data and keep it synced to reality
EC | 29 |  | 8 |  | Finished in Sprint 6 | Manager | Edit a container | Improve our data and keep it synced to reality
ET | 30 |  | 8 |  | Finished in Sprint 6 | Manager | Edit a new topping | Improve our data and keep it synced to reality
ROA | 31 |  | 3 |  | Finished in Sprint 6 | Manager | Add Order Report option to show completed as well as pending orders | Review our order history seeking patterns to understand how to improve efficiency and profit
SALL | 32 |  | 5 |  |  | Owner | Save all data to a specified file | Franchise my company
LALL | 33 |  | 5 |  |  | Owner | Load data from a specified file | Franchise my company
CENEW | 34 |  | 13 |  |  | Owner | Create a new franchise | Franchise my company
XI | 35 |  | 21 |  |  | Manager | Retire an item (no longer enable its selection for a new order, but keep in reports) | Remove items no longer offered from the menu
XT | 36 |  | 13 |  |  | Manager | Suspend a server (no longer allow their selection for an order or restock, but keep in reports) | Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT | 37 |  | 5 |  |  | Manager | Restore a server | Add a former team member tack into service
CP&L | 38 |  | 21 |  |  | Owner | Create a corporate Profit & Loss statement, showing all income, expenses, and total profit for all franchises in aggregate | Keep track of our overall financial situation | This may require maintaining a list of all franchisee files, loading the data in sequence or simultaneously, and then calculating a single report across them all
HH | 39 |  | 21 |  |  | Manager | Automatically change to “happy hour” prices between 4 and 6 pm each day, then back to regular prices | Increase business during the slow period before supper | Include an override, so that the feature can be demonstrated regardless of the time of day
MWT | 40 |  | 34 |  |  | Server | See a table to the main window showing all orders in the Unfilled or Filled state | Easily monitor the backlog of preparation and collecting payment
MWTS | 41 |  | 21 |  |  | Manager | Scroll the main window table when it won’t all fit on the screen | Handle rush hour more efficiently

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2017-10-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-10-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 8
Day 1 Left | 7 | 1
Day 2 Left | 1 | 6
Day 3 Left | 0 | 1
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  | BC | Complete Use Case diagram | Completed Day 1
2 |  | BC | Complete Class diagram | Completed Day 2
3 |  | BC | Complete Sequence diagram | Completed Day 2
4 |  | BC | Implement classes for sprint one | Completed Day 2
5 |  | BC | Create a new flavor | Completed Day 2
6 |  | BC | Create a new container | Completed Day 2
7 |  | BC | Create a new topping | Completed Day 2
8 |  | BC | Convert to GUI | Completed Day 3
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2017-10-26 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-02
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 9 | 4
Day 2 Left | 4 | 5
Day 3 Left | 2 | 2
Day 4 Left | -1 | 3
Day 5 Left | -1 | 0
Day 6 Left | -1 | 0
Day 7 Left | -1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  | BC | Make it so there is a global container, flavors, toppings choice | Completed Day 1
2 |  | BC | Allow the manager to create a server and list them | Completed Day 1 | There are also built in defaults
3 |  | BC | Allow the server to choose a container for a serving | Completed Day 1
4 |  | BC | Allow the server to choose number of scoops for container | Completed Day 1
5 |  | BC | Allow the server to choose flavor for each scoop | Completed Day 2
6 |  | BC | Allow the server to choose toppings for each scoop | Completed Day 2
7 |  | BC | Allow the server to create a customer | Completed Day 2
8 |  | BC | Allow the server to identify if the customer belongs to a particular server | Completed Day 2
9 |  | BC | Allow the server to create a serving for him/herself or a specific customer | Completed Day 2
10 |  | BC | Allow the customer to view the serving created for them by server | Completed Day 3
11 |  | BC | Allow the server to view their own servings | Completed Day 3 | that's if they made a serving for themselves
12 |  | BC | Added polymorphism (to_string method for items) | Completed Day 4
13 |  | BC | Added toolbar buttons | Completed Day 4
14 |  |  |  | Completed Day 4
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-11-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 19
Day 1 Left | 12 | 7
Day 2 Left | 2 | 10
Day 3 Left | 1 | 1
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | Create order as a server
2 |  |  | First allow servings to be chosen for order | Completed Day 1
3 |  |  | Remove servings from servings list that are added to order | Completed Day 1
4 |  |  | Push servings into order object that contains servings vector | Completed Day 1
5 |  |  | Rewrite program without pointers (too much confusion) | Completed Day 1
6 |  |  | Use return statements and reassign anything that changes | Completed Day 1
7 |  |  | Fix create serving so that it works with multiple cust under a serv | Completed Day 1
8 |  |  | Add a view order | Completed Day 1
9 |  |  | Add create serving for customer | Completed Day 2
10 |  |  | Handle situations where the customer has a server, doesn’t have a server | Completed Day 2
11 |  |  | Handle situations where customer self servs with/without server | Completed Day 2
12 |  |  | Allow server and customer to both create servings | Completed Day 2
13 |  |  | Allow viewing of the serving | Completed Day 2
14 |  |  | Begin create order for customer | Completed Day 2
15 |  |  | Remove servings to be added into an order | Completed Day 2
16 |  |  | handle situations where a customer has a server but is making the order | Completed Day 2
17 |  |  | Allow either one to make the order if assigned | Completed Day 2
18 |  |  | Add a view order | Completed Day 2
19 |  |  | Operator overloading added for a few comparisons | Completed Day 3
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-11-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-16
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 23
Day 1 Left | 18 | 5
Day 2 Left | 10 | 8
Day 3 Left | 0 | 10
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | Add file save for toppings | Completed Day 1
2 |  |  | Add file save for scoops | Completed Day 1
3 |  |  | Add file save for containers | Completed Day 1
4 |  |  | Add file save for customers | Completed Day 1
5 |  |  | Add file save for servers | Completed Day 1
6 |  |  | Add file save for servings | Completed Day 2
7 |  |  | Add file save for orders | Completed Day 2
8 |  |  | Add file load for toppings | Completed Day 2
9 |  |  | Add file load for scoops | Completed Day 2
10 |  |  | Add file load for containers | Completed Day 2
11 |  |  | Add file load for servings | Completed Day 2
12 |  |  | Add file load customers | Completed Day 2
13 |  |  | Add file load for servers | Completed Day 2
14 |  |  | Add file load for customers | Completed Day 3
15 |  |  | Add price calculations for each item | Completed Day 3
16 |  |  | Add wholesale calculations for each item | Completed Day 3
17 |  |  | Add total price calculation for emporium | Completed Day 3
18 |  |  | Add total wholesale calculation for emporium | Completed Day 3
19 |  |  | Add profit | Completed Day 3
20 |  |  | Add cash register for manager | Completed Day 3
21 |  |  | Add state machine for states of an order | Completed Day 3
22 |  |  | Add state machine diagram | Completed Day 3
23 |  |  | Add readme text | Completed Day 3
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-11-16 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-23
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 3
Day 1 Left | 1 | 2
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | Make it so that a server can check orders in the queue and see them | Completed Day 1
2 |  |  | The viewing serving and view order for server and customer were added already mostly | Completed Day 1
3 |  |  | Added regex validation
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-11-23 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 11
Day 1 Left | 10 | 1
Day 2 Left | 6 | 4
Day 3 Left | 5 | 1
Day 4 Left | 0 | 5
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | Create code to insert an image into a box | Completed Day 1
2 |  |  | Added code so image loads inside a box | Completed Day 2
3 |  |  | Edit images to be the correct size | Completed Day 2
4 |  |  | Added a credits tab to menu bar so the source links are available | Completed Day 2
5 |  |  | Added menu, container, scoop, and toppings images to program | Completed Day 2
6 |  |  | Added ability to change server salary | Completed Day 3
7 |  |  | Add edit ice cream flavor/scoop | Completed Day 4
8 |  |  | Add edit container | Completed Day 4
9 |  |  | Add edit topping | Completed Day 4
10 |  |  | Update UML | Completed Day 4
11 |  |  | Brochure | Completed Day 4
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84